SYNERGY NETWORK DAG Validator Cluster Integration PART 3: Deployment, Operations & Deliverables ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ Covers:; Release Gates, Pre-Deployment, Operations, Deliverables. Security Baseline:; Synergy Security Spec v1.3 — Mandatory Compliance. Prerequisites:; Part 1 and Part 2 complete and signed off. Prepared:; April 2026. ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ Part 3 of 3 — Final document in the DAG Integration series

# Table of Contents

Table of Contents	1

Release Gate Criteria	1

Pre-Deployment Checklist	1

16.1 Code Readiness	1

16.2 Security Readiness	1

16.3 Infrastructure & Configuration Readiness	1

16.4 Operational Readiness	1

16.5 Activation Procedure	1

16.6 Rollback Triggers	1

Operational Runbook	1

17.1 Checking DAG Health	1

17.2 Handling a DAG Integrity Failure	1

17.3 Managing DAG Storage	1

17.4 Epoch Boundary Procedure	1

17.5 Finality Disambiguation — Operator Protocol	1

30/60/90-Day Milestone Plan	1

Day 30 — Certified DAG in One Cluster	1

Day 60 — Block Proposal from DAG + Consensus Binding	1

Day 90 — Full Testnet-Beta DAG Operational + Adversarial Simulation	1

Complete Deliverables Matrix	1

19.1 Documentation Deliverables	1

19.2 Code Deliverables	1

19.3 Test Deliverables	1

Control Panel (Jarvis) DAG Integration	1

20.1 Required Jarvis DAG Features	1

20.2 DAG Bounded Workflows	1

Whitepaper Update Summary	1

21.1 02-system-architecture.md — System Architecture	1

21.2 03-proof-of-synergy-consensus.md — PoSy Consensus	1

21.3 09-threat-model-security-patent-relevant-effects.md — Threat Model	1

21.4 10-roadmap-and-strategic-outlook.md — Roadmap	1

21.5 Whitepaper Update Checklist	1

Specification Cross-Reference and Authority	1

SECTION 15

# Release Gate Criteria

Eight binary release gates govern the progression from Testnet-Beta DAG development to production activation. Each gate is pass/fail — there is no partial credit. All gates must pass before dag.enabled is set to true on any Testnet-Beta validator cluster. Gate 8 (Audit Gate) must pass before any mainnet consideration begins.

|  | Gate Hierarchy Gates are ordered by dependency: a higher-numbered gate cannot be attempted until all lower-numbered gates have passed. Gate sign-offs are documented in the DAG Release Gate Registry, a living document maintained by the security lead. Verbal or informal approvals are not accepted. |
| --- | --- |

Gate 1: Specification Gate ¦ Owner: Lead Protocol Engineer + Security Lead - All 6 ADRs (ADR-001 through ADR-006) formally approved and published in the ADR registry - Cluster size canonicalized: MAX_CLUSTER_SIZE, config default, and consensus fallback all equal 7 - DAG schemas frozen: all 6 canonical object type schemas published in protocol type registry with version numbers - Epoch duration decision documented in a signed network configuration ADR - EntropyBeacon determinism fix: wall-clock removed, unit test passing - [dag] configuration namespace fully specified in config/mod.rs with all 18 parameters

Gate 2: Protocol Safety Gate ¦ Owner: Lead Protocol Engineer - No uncertified vertex can appear in any OrderingCut — enforced by proposer gate and unit test - QC path (dual_quorum.rs) is unchanged: diff review confirms zero modifications to QC verification logic - No conflicting OrderingCuts possible for the same round — determinism test with identical certified frontier input - Block header DAG roots are informational only: blocks still require full QC vote; QC cannot be bypassed via DAG - Equivocation detection works: same-author same-round second vertex triggers evidence and quarantine - Cluster-scope gossip filter works: DAG messages from non-cluster peers rejected at P2P ingress

Gate 3: Availability Gate ¦ Owner: Protocol Engineering - Missing-parent fetch protocol works: validator receiving vertex with unknown parent fetches parent correctly - Archive/audit node DAG reconstruction demonstrated: fresh archive node reconstructs DAG from checkpoints - Availability certification loop produces DagCertificate within expected latency under normal conditions - Blob withholding scenario (1 of 7 withholds): remaining 5 certify; certificate formed; ordering proceeds - Certification timeout-to-mempool: batch unable to achieve certification returns to flat mempool - Blob persistence: certified blobs retained in hot storage for gc_finality_depth rounds after certification

Gate 4: Security Gate ¦ Owner: Security Lead - All 5 DAG evidence types (equivocation, certificate fraud, data withholding, censorship, replay/stale) triggered successfully in adversarial simulation - All 5 evidence types submitted to slashing subsystem; validator stake reduction confirmed in state for each - All 8 non-negotiable security controls (Part 2, Section 13.2) verified with unit tests - Security Spec v1.3 alignment matrix signed off by security lead - Internal adversarial simulation report completed and signed off by security lead - No critical security issues outstanding from security review session

Gate 5: Operational Gate ¦ Owner: Validator Operations + Control Panel Engineering - Control Panel (Jarvis) displays DAG health status, quarantine status, and evidence bundles - All 10 DAG RPC methods return correct data in all error and success cases - DAG-specific logging: all vertex, certificate, cut, and evidence events logged with structured fields - Operator documentation: DAG status vs. QC finality is clearly distinguished in all operator-facing interfaces - GC daemon (src/dag/gc.rs) runs correctly: hot storage bounded at gc_finality_depth rounds - Role profiles (DA, archive, audit) have explicit and correctly enforced DAG data access policies

Gate 6: Exposure Gate ¦ Owner: Security Lead + Networking - Network audit confirms no new public-facing ports opened by DAG implementation - All DAG P2P messages use the existing authenticated P2P layer — no unauthenticated DAG surfaces - Cluster-scope filter prevents raw vertex gossip from crossing cluster boundaries — confirmed by network trace - ClusterCheckpoint signature verification enforced for all cross-cluster checkpoint consumers - dag.enabled = false confirmed as default in shipped configuration; must be explicitly set to true by operator - Any public-facing DAG RPC method that could reveal pre-ordering transaction information reviewed and confirmed safe

Gate 7: Audit Gate ¦ Owner: Security Lead + External Auditor - Third-party security review engagement scheduled and confirmed (vendor, scope, timeline) - Third-party review completed for at minimum: DAG object model, availability certification, evidence types, cluster gossip filter - All critical and high findings from third-party review resolved or have accepted risk with documented rationale - Third-party review report published internally - Adversarial simulation repeated by independent team after all review findings are resolved - Final security lead sign-off on complete DAG stack for Testnet-Beta activation

Gate 8: Economic & Accountability Gate ¦ Owner: Protocol Engineering + Economics - All 5 DAG slashing types implemented and slashable in the live Testnet-Beta validator set - Synergy Score degradation correctly applied for DAG infractions (not just stake slashing) - DAG evidence export to external monitoring tools confirmed working - Validator compensation policy for DAG participation (availability receipt issuance) defined and documented - Epoch-boundary DAG archival and retention policy tested over at least 3 full epoch cycles on Testnet-Beta - Economic modeling review: DAG incentive structure reviewed for unintended gaming vectors

SECTION 16

# Pre-Deployment Checklist

The following pre-deployment checklist must be completed before setting dag.enabled = true on any production Testnet-Beta validator. This checklist is cumulative with all phase checklists in Part 2. If any item cannot be checked, deployment must be halted and the issue resolved first.

## 16.1 Code Readiness

- All Phase 0-4 implementation checklists (Part 2, Section 14) complete and verified

- All Priority 1 files (Part 2, Section 10.1) implemented, code-reviewed, and merged

- No open CRITICAL or HIGH severity bugs in DAG components

- CI pipeline green: all unit tests, integration tests, and schema validation tests passing

- Static analysis: no plaintext transaction bytes in DagVertex confirmed by CI rule

- Dependency audit: all cryptographic dependencies are post-quantum (ML-DSA-65, ML-KEM-768, Blake3)

- Feature flag: dag.enabled = false in default shipped configuration (not just in tests)

## 16.2 Security Readiness

- All 8 release gates passed and documented in the DAG Release Gate Registry

- Third-party security audit complete (Gate 7) — report published internally

- All critical and high security findings resolved

- Security lead final sign-off obtained — dated, named, written

- Adversarial simulation report (Phase 4) approved by security lead

- Non-negotiable security controls re-verified post-audit on clean codebase

- Key management: ML-DSA key registration for all participating validators confirmed

- Epoch key management: ML-KEM batch decryption key release mechanism tested end-to-end

## 16.3 Infrastructure & Configuration Readiness

- Testnet-Beta cluster topology confirmed: n=7 per cluster, beta documentation updated

- All validators running the DAG-enabled node version (confirmed by node version check)

- All validators have explicit [dag] configuration blocks in their node config files

- dag.enabled = false on all nodes pre-activation (activation is explicit, not default)

- Blob storage capacity provisioned on all participating validators for DAG artifact retention

- GC daemon (src/dag/gc.rs) confirmed running on all nodes

- Network capacity assessment: DAG gossip overhead within cluster P2P budget

- Monitoring dashboards (Control Panel / Jarvis) connected and displaying DAG metrics

## 16.4 Operational Readiness

- Operator runbook (Section 17 of this document) reviewed by all validator operators

- Rollback plan documented and tested: how to disable DAG (dag.enabled = false) without block production outage

- On-call rotation confirmed: at least one engineer familiar with DAG internals on call during activation

- Incident response procedure confirmed: DAG-specific alerts defined in monitoring system

- Validator operators notified of activation: timing, expected behavior changes, monitoring guidance

- Control Panel (Jarvis) DAG quarantine workflow tested: can quarantine a misbehaving peer without validator restart

## 16.5 Activation Procedure

Activation must follow this exact sequence. Do not skip steps or change the order.

| Step | Action |
| --- | --- |
| Step 1 | Deploy DAG-enabled node version to all cluster validators simultaneously (not one by one) |
| Step 2 | Verify all nodes start successfully with dag.enabled = false; confirm DAG subsystem is loaded but inactive |
| Step 3 | Enable DAG on a single designated canary validator: set dag.enabled = true; monitor for 30 minutes |
| Step 4 | Verify canary: synergy_getDagStatus returns enabled; synergy_getClusterDagHealth returns healthy |
| Step 5 | If canary is healthy, enable DAG on remaining cluster validators one at a time; 5-minute gap between each |
| Step 6 | Verify full cluster DAG: synergy_getClusterDagHead returns current round with all validators active |
| Step 7 | Monitor for 60 minutes: error rate nominal, DAG certificate formation rate > 95%, no quarantine events |
| Step 8 | Confirm first DagCertificate-backed block committed: block header contains valid ordering_cut_root |
| Step 9 | Document activation: timestamp, confirming engineer name, all validators active, gate registry updated |

## 16.6 Rollback Triggers

|  | Rollback Policy If any rollback trigger is hit, immediately set dag.enabled = false on all cluster validators. The node will fall back to flat-mempool block production mode. No QC path disruption should occur. Document the event, preserve logs, and do not re-enable DAG until the root cause is identified and fixed. |
| --- | --- |

- DAG certificate formation rate drops below 80% for more than 5 consecutive rounds

- Any block is produced with an invalid or inconsistent ordering_cut_root

- QC error rate increases by more than 5% above baseline after DAG activation

- Any node hits DAG graph integrity failure that triggers quarantine of more than 1 peer simultaneously

- Any evidence of encrypted batch decryption before QC finalization of the containing OrderingCut

- Any unauthenticated DAG message is accepted (authentication bypass detected)

- Any cross-cluster raw vertex gossip detected in network traces

- Memory or disk usage on any validator node increases by more than 50% above pre-DAG baseline

SECTION 17

# Operational Runbook

This runbook provides procedures for common operational tasks related to the Synergy DAG sublayer. It is intended for validator operators and on-call engineers. All procedures assume the DAG is enabled (dag.enabled = true). For emergency procedures, see Section 16.6 (Rollback Triggers).

## 17.1 Checking DAG Health

| Task | RPC Method | Output |
| --- | --- | --- |
| Check overall DAG status | synergy_getDagStatus | Returns: enabled, mode, current round, certified frontier size, last cut round |
| Check cluster DAG head | synergy_getClusterDagHead | Returns: highest certified round, DAG watermark, cluster_id, epoch_id |
| Check per-validator activity | synergy_getValidatorDagActivity | Returns: vertex production rate, receipt rate, certificate participation per validator (requires audit role) |
| Check cluster health metrics | synergy_getClusterDagHealth | Returns: per-validator availability participation rate, late/missing vertex rate, frontier diversity score |
| Check evidence for conflicts | synergy_getDagConflicts | Returns: list of detected equivocations and their evidence submission status |

## 17.2 Handling a DAG Integrity Failure

When a validator detects a DAG graph integrity failure (e.g., a vertex with a forged parent reference, or an equivocation), the following procedure applies:

- The node automatically quarantines the offending peer (quarantine_on_integrity_failure = true must be set)

- The node continues accepting DAG traffic from non-quarantined peers

- The operator is notified via a structured log event and a Control Panel (Jarvis) alert

- Operator action: call synergy_getDagConflicts to confirm the equivocation evidence

- Operator action: call synergy_getDagEvidence to retrieve the evidence bundle

- Operator action: verify the evidence bundle is correct and submit to the slashing subsystem if not already auto-submitted

- Operator action: document the incident in the DAG incident log

- If more than 1 peer is quarantined simultaneously, consider rollback (Section 16.6)

## 17.3 Managing DAG Storage

- Check retention status: synergy_getDagRetentionStatus — returns hot storage rounds, archive epochs, last GC run

- GC daemon runs automatically at configurable interval; hot storage bounded to gc_finality_depth = 256 rounds

- Archive nodes retain full DAG history; hot nodes retain only gc_finality_depth rounds

- If hot storage exceeds expected size, check for GC daemon health and verify gc_finality_depth is set correctly

- Epoch-boundary archival: verify ClusterCheckpoint is produced and signed before the new epoch DAG starts

- Full DAG history: only accessible on archive/audit role nodes; operators must not expect full history on validators

## 17.4 Epoch Boundary Procedure

At each epoch boundary, the following procedure occurs automatically. Operators should monitor for completion:

- Phase 1: DAG for the ending epoch is sealed — no new vertices accepted for the ending epoch

- Phase 2: Epoch-boundary ClusterCheckpoint is produced and aggregated (requires 2f+1 = 5 validator signatures at n=7)

- Phase 3: ClusterCheckpoint is QC-finalized before the new epoch's DAG begins

- Phase 4: New epoch begins with empty DAG and new cluster membership (if rotation occurred)

- Operator check: synergy_getClusterDagHead should show new epoch_id after boundary

- Operator check: synergy_getDagRetentionStatus should show previous epoch moved to archive tier

- If ClusterCheckpoint fails to achieve 2f+1 signatures: escalate; do not start new epoch DAG without sealed checkpoint

## 17.5 Finality Disambiguation — Operator Protocol

|  | Critical Operator Knowledge DAG availability status and QC finality are distinct concepts. A transaction is 'available' when its batch is certified (DagCertificate formed). A transaction is 'settled' ONLY when the QC is finalized for the block containing the OrderingCut that included it. Always use the is_qc_finalized field in RPC responses to distinguish these states. |
| --- | --- |

| State | Meaning | Is Transaction Settled? |
| --- | --- | --- |
| batch_certified | Transaction data available to cluster validators; DagCertificate formed | No — batch is available, not settled |
| in_ordering_cut | Transaction included in an OrderingCut referenced in a proposed block | No — block not yet QC-voted |
| block_proposed | Block containing the OrderingCut has been proposed by the proposer | No — awaiting QC votes |
| qc_finalized | Block has received 2f+1 QC votes and is committed to the chain | YES — this is the only settled state |

SECTION 18

# 30/60/90-Day Milestone Plan

The following milestone plan targets the first 90 days of DAG implementation work starting from Phase 0. Milestones are cumulative — Day 60 milestones build on Day 30 milestones. All milestones assume Part 1 deliverables (ADR pack, schema pack, config namespace) are complete before the clock starts.

## Day 30 — Certified DAG in One Cluster

Target: A certified DAG is operational in one Testnet-Beta validator cluster (availability-first mode, not yet integrated into block production). Phase 0 and Phase 1 complete, Phase 2 underway.

| Milestone | Deliverable | Success Criteria | Owner |
| --- | --- | --- | --- |
| D30-1 | Phase 0 complete: all ADRs approved, parameter canonicalization done, [dag] config namespace live | CI gate green; ADR registry populated; cluster size = 7 in all three constants | Lead Engineer |
| D30-2 | All 6 canonical DAG object types implemented in src/dag/types.rs with full test coverage | Round-trip serialization tests passing; rejection tests passing; schema registry updated | Protocol Engineering |
| D30-3 | DAG storage layer (src/dag/storage.rs) implemented with epoch-indexed structure | Epoch pruning test passing; hot/archive tier interface defined | Protocol Engineering |
| D30-4 | Batch builder implemented: ML-KEM-768 encrypted DagBatch production working | Batch builder produces encrypted blobs; no plaintext shortcut path; CI static analysis confirms | Protocol Engineering |
| D30-5 | Availability certification loop functional: DagCertificate formed from AvailabilityReceipts | Certification at 5 receipts (2f+1, n=7) working; timeout-to-mempool tested | Protocol Engineering |
| D30-6 | Equivocation detection tested: same-author same-round triggers evidence emission | Evidence emitted correctly; peer quarantined; unit test passing | Protocol Engineering |

## Day 60 — Block Proposal from DAG + Consensus Binding

Target: The DAG is integrated into block production. Blocks proposed from OrderingCuts. Block headers contain DAG roots. Validators verify DAG roots. Phase 3 complete, Phase 4 underway.

| Milestone | Deliverable | Success Criteria | Owner |
| --- | --- | --- | --- |
| D60-1 | DAG wire message types in messages.rs; cluster-scoped gossip filter live on Testnet-Beta | Cross-cluster DAG message rejection confirmed in network trace; all 6 message types gossiping in-cluster | Protocol Engineering |
| D60-2 | Block proposer integrated with DAG: OrderingCuts drive block assembly | Blocks contain ordering_cut_root in header; proposer rejects uncertified vertices; QC voting unchanged | Protocol Engineering |
| D60-3 | Validator block verification of DAG roots working | Validators reject blocks with invalid ordering_cut_root; block with wrong root rejected in integration test | Protocol Engineering |
| D60-4 | 8 Phase 3 DAG RPC methods implemented and returning correct data | All 8 methods tested with both success and error cases; Control Panel consuming RPC data | Protocol Engineering |
| D60-5 | DAG evidence types 1-3 (equivocation, certificate fraud, data withholding) implemented and slashable | Slashing hook fires for each type; stake reduction confirmed in Testnet-Beta state | Protocol Engineering |
| D60-6 | All 8 non-negotiable security controls verified with unit tests | Security lead signs off on control verification; no controls failing | Security Lead |

## Day 90 — Full Testnet-Beta DAG Operational + Adversarial Simulation

Target: All Phase 0-4 work complete. All 8 release gates passed or on track. Internal adversarial simulation complete. External audit engaged. dag.enabled = true on at least one Testnet-Beta cluster.

| Milestone | Deliverable | Success Criteria | Owner |
| --- | --- | --- | --- |
| D90-1 | All 5 DAG evidence types implemented; slashing live for all 5 types | All 5 slashing events triggered in adversarial simulation; simulation report signed off by security lead | Security Lead |
| D90-2 | All 10 DAG RPC methods complete; Control Panel DAG integration complete | All 10 methods returning correct data; Control Panel quarantine workflow and evidence export tested | Engineering + Ops |
| D90-3 | Internal adversarial simulation: all 10 threats in threat matrix tested | Simulation report produced; all threats have a verified control; no unmitigated critical findings | Security Lead |
| D90-4 | All 8 release gates passed and documented in DAG Release Gate Registry | Release gate registry complete with dates and owner signatures for all 8 gates | Security Lead |
| D90-5 | External security audit engaged: scope, vendor, timeline confirmed | Audit contract signed; audit kick-off meeting completed; scope document approved | Security Lead |
| D90-6 | dag.enabled = true on one Testnet-Beta cluster after activation procedure (Section 16.5) | Activation log entry; 60-minute post-activation monitoring nominal; no rollback triggers hit | Validator Ops |

SECTION 19

# Complete Deliverables Matrix

The following matrix is the authoritative list of all deliverables for the Synergy DAG Validator Cluster Integration. Every deliverable has a defined artifact, location, owner, and phase gate. This matrix is the primary tracking artifact for management-level reporting.

## 19.1 Documentation Deliverables

| Deliverable | Artifact | Location | Owner | Phase Gate |
| --- | --- | --- | --- | --- |
| ADR Pack (ADR-001 to ADR-006) | 6 ADR documents | docs/adr/ | Lead Engineer | Phase 0 |
| Parameter Canonicalization Report | Written confirmation of all parameter fixes | docs/dag/canonicalization.md | Protocol Eng. | Phase 0 |
| Security Alignment Matrix | v1.3 alignment per security category | docs/dag/security-alignment.md | Security Lead | Phase 0 |
| DAG Schema Pack | 6 canonical object schemas with version numbers | Protocol type registry + docs/dag/schemas/ | Protocol Eng. | Phase 1 |
| DAG Configuration Reference | [dag] namespace documentation | docs/dag/configuration.md | Protocol Eng. | Phase 0 |
| DAG RPC Reference | 10 method specifications with request/response examples | docs/rpc/dag-methods.md | Protocol Eng. | Phase 4 |
| Adversarial Simulation Report | All 5 evidence types + 10 threats tested, findings, resolutions | docs/dag/adversarial-simulation.md | Security Lead | Phase 4 |
| Release Gate Registry | 8 gates with dates, owners, sign-off status | docs/dag/release-gates.md | Security Lead | Ongoing |
| Operator Runbook | Procedures for all common DAG operational tasks | This document, Section 17 | Validator Ops | Phase 3 |
| 30/60/90-Day Progress Reports | Written milestone status at each checkpoint | docs/dag/milestones/ | Lead Engineer | Ongoing |
| Third-Party Audit Report | External security review of complete DAG stack | Internal — restricted access | External Auditor | Gate 7 |
| Whitepaper DAG Update | Updated whitepaper sections: Architecture, PoSy Consensus, Threat Model, Roadmap | synergy-network-whitepaper/ | Protocol Eng. | Phase 3 |

## 19.2 Code Deliverables

| File / Module | Description | Owner | Phase Gate |
| --- | --- | --- | --- |
| src/dag/types.rs | All 6 canonical DAG object types with validation | Protocol Engineering | Phase 1 |
| src/dag/storage.rs | Epoch-indexed DAG storage with GC | Protocol Engineering | Phase 1 |
| src/dag/batch_builder.rs | ML-KEM-768 encrypted DagBatch builder | Protocol Engineering | Phase 1 |
| src/dag/availability.rs | Availability receipt loop and certificate formation | Protocol Engineering | Phase 2 |
| src/dag/cut_builder.rs | Deterministic OrderingCut construction | Protocol Engineering | Phase 3 |
| src/dag/evidence.rs | All 5 DAG evidence types + slashing integration | Protocol Engineering | Phase 4 |
| src/dag/checkpoint.rs | ClusterCheckpoint production (Post-Beta Phase 5) | Protocol Engineering | Phase 5 |
| src/dag/gc.rs | GC daemon: hot-to-archive migration, retention policy | Protocol Engineering | Phase 3 |
| src/consensus/consensus_algorithm.rs (modified) | DAG manager integration, certified-frontier selection | Protocol Engineering | Phase 3 |
| src/block.rs (modified) | ordering_cut_root and availability_commitment fields | Protocol Engineering | Phase 3 |
| src/p2p/messages.rs (modified) | 6 DAG wire message types + capability flags | Protocol Engineering | Phase 3 |
| src/p2p/networking.rs (modified) | Cluster-scoped gossip filter, DAG rate limiting | Protocol Engineering | Phase 3 |
| src/validator.rs (modified) | Cluster size fix, DAG production rights, slashing hooks | Protocol Engineering | Phase 0 |
| src/config/mod.rs (modified) | [dag] namespace with 18 parameters | Protocol Engineering | Phase 0 |
| src/consensus/entropy.rs (modified) | Deterministic entropy (wall-clock removed) | Protocol Engineering | Phase 0 |
| src/rpc/rpc_server.rs (modified) | 10 DAG RPC methods | Protocol Engineering | Phase 3-4 |
| src/consensus/cartel_detection.rs (modified) | DAG-native cartel detection signals | Protocol Engineering | Phase 4 |

## 19.3 Test Deliverables

| Test | Coverage | Owner | Phase Gate |
| --- | --- | --- | --- |
| Unit test suite: 6 DAG object types | Schema validation, round-trip, rejection tests for all 6 types | Protocol Engineering | Phase 1 |
| Unit test: DagCertificate threshold at n=7 | Certificate formed at 5 receipts; fails at 4 | Protocol Engineering | Phase 2 |
| Unit test: Equivocation detection | Same-author same-round second vertex triggers evidence | Protocol Engineering | Phase 1 |
| Unit test: Availability gate in proposer | Uncertified vertex in OrderingCut returns explicit error | Protocol Engineering | Phase 2 |
| Unit test: Deterministic OrderingCut | Identical certified frontier produces identical cut at two validators | Protocol Engineering | Phase 3 |
| Unit test: Cluster gossip filter | Out-of-cluster DAG messages rejected at P2P ingress | Protocol Engineering | Phase 3 |
| Unit test: EntropyBeacon determinism | Identical block-hash input produces identical entropy output | Protocol Engineering | Phase 0 |
| Unit test: Non-negotiable security controls | 8 controls each with a dedicated unit test | Protocol Engineering | Phase 3 |
| Adversarial test: blob withholding (1 of 7) | 5 remaining certify; certificate formed; ordering proceeds | Protocol Engineering | Phase 2 |
| Adversarial test: all 5 DAG evidence types | Each evidence type triggered and slashing hook confirmed | Security Lead | Phase 4 |
| Adversarial test: all 10 threats | Each threat in threat matrix tested; results in simulation report | Security Lead | Phase 4 |
| Integration test: end-to-end block with DAG | Block with DAG ordering_cut_root QC-finalized on Testnet-Beta | Protocol Engineering | Phase 3 |
| CI rule: no plaintext in DagVertex | Static analysis rejects code with plaintext transaction bytes in vertex | Protocol Engineering | Phase 1 |
| CI rule: ADR compliance checks | Automated checks enforcing each ADR at code level | Protocol Engineering | Phase 0 |

SECTION 20

# Control Panel (Jarvis) DAG Integration

The Synergy Control Panel (Jarvis) must be updated to support DAG operations. This is an operability deliverable, not a protocol deliverable — it does not affect consensus but is required for operators to manage the DAG in production. All Jarvis DAG features must be complete before Gate 5 (Operational Gate) can pass.

## 20.1 Required Jarvis DAG Features

| Feature | Description | Phase Gate |
| --- | --- | --- |
| DAG Health Dashboard | Real-time display of synergy_getClusterDagHealth data: per-validator participation rate, certificate formation rate, frontier diversity score | Phase 3 |
| DAG Status Panel | Display of synergy_getDagStatus: enabled/disabled, mode, current round, frontier size, last cut round | Phase 3 |
| Evidence Feed | Real-time feed of synergy_getDagEvidence: evidence type, offending validator, severity, slashing submission status | Phase 4 |
| Quarantine Management | Ability to view quarantined peers, view quarantine reason, manually lift quarantine after review (requires operator role) | Phase 4 |
| Validator Activity View | Display of synergy_getValidatorDagActivity: vertex rate, receipt rate, certificate participation per validator (audit role only) | Phase 4 |
| Finality Status Indicator | Clear visual distinction between 'DAG Certified' and 'QC Finalized' transaction states in all block/tx explorer views | Phase 3 |
| Retention Status | Display of synergy_getDagRetentionStatus: hot storage rounds, archive epochs, GC last run | Phase 3 |
| Parameter Validation | Validation UI for [dag] configuration parameters: warns if any non-negotiable parameter is set incorrectly | Phase 0 |

## 20.2 DAG Bounded Workflows

The following workflows must be bounded by DAG rollout stages in Jarvis. These workflows become available only when the corresponding phase gate has passed — they must not be exposed to operators prematurely.

- DAG Activation workflow (set dag.enabled = true): available only after all 8 release gates pass

- Evidence export workflow: available after Phase 4 completes

- Cross-cluster checkpoint view: available after Phase 5 (Post-Beta)

- Execution-DAG view: available after Phase 8 (Post-Beta)

- Quarantine lift workflow: available after Phase 4; requires operator role and evidence acknowledgment

SECTION 21

# Whitepaper Update Summary

The Synergy Network Whitepaper must be updated to reflect the DAG architecture additions. Updates are scoped to four existing whitepaper sections. The whitepaper updates are informational (they describe the design and rationale) rather than normative (the specification documents in Parts 1-3 are normative).

|  | Whitepaper vs. Specification The three-part DAG Integration Specification (Parts 1-3) is the normative implementation reference. The whitepaper updates describe the architectural intent for external audiences. In any conflict between the whitepaper and the specification, the specification takes precedence. |
| --- | --- |

## 21.1 02-system-architecture.md — System Architecture

Add a new sub-section 3.7: DAG Sublayer. This section describes the cluster-local DAG as an extension of the Consensus Plane, explains the five architectural invariants, and clarifies that the DAG is a data plane, not a finality mechanism. Include a simplified data flow diagram (the text-art diagram from Part 1, Section 4.2). Update Section 3.2 to note that the Consensus Plane now includes a DAG dissemination sublayer.

- Add Section 3.7: The Cluster-Local DAG Sublayer

- Update Section 3.2 Consensus Plane description to include DAG dissemination

- Add simplified target data flow diagram

- Add key DAG design principle: availability before ordering

- Add cross-reference to Section 3.3 (Cryptographic Plane): all DAG signatures use Aegis/ML-DSA

## 21.2 03-proof-of-synergy-consensus.md — PoSy Consensus

Add a new sub-section 6.9: DAG Mempool and Pre-Ordering. This section explains how the cluster-local DAG improves transaction dissemination and pre-ordering while leaving PoSy QC finality entirely unchanged. Include the six canonical DAG object types (as high-level descriptions, not full schema). Reference ADR-001 as the finality-stays-QC-based decision.

- Add Section 6.9: Cluster-Local DAG Mempool and Pre-Ordering

- Describe high-level flow: encrypted batch -> DAG vertex -> availability certification -> ordering cut -> block proposal -> QC finality

- Add: 'The DAG does not alter PoSy finality. QC certification remains the sole settlement mechanism.'

- Add high-level description of the 6 canonical DAG objects

- Update Section 6.3 (Cooperative Validator Clustering) to note cluster = DAG scope boundary

## 21.3 09-threat-model-security-patent-relevant-effects.md — Threat Model

Add a new sub-section covering DAG-specific threat categories. This section introduces the three DAG security categories from Security Spec v1.3 (DAG-1: Spam/Replay, DAG-2: Data Withholding, DAG-3: Equivocation) and explains how the mandatory controls (encrypted batches, 2f+1 availability certification, one-author-one-vertex-per-round) address each threat.

- Add DAG-specific threat section with 3 primary threat categories

- Explain encrypted batch invariant: why the DAG never exposes plaintext transaction data

- Explain 2f+1 availability certification: why data withholding is prevented with this threshold

- Explain equivocation detection: one-author-one-vertex-per-round as a safety primitive

- Cross-reference Security Spec v1.3 as the normative threat definition document

## 21.4 10-roadmap-and-strategic-outlook.md — Roadmap

Add a DAG integration milestone to the roadmap section. Reference the 8-phase plan and the 30/60/90-day milestones. State that the cluster-local DAG is a Testnet-Beta phase objective and that mainnet consideration requires completion of all 8 release gates including third-party security audit.

- Add DAG Validator Cluster Architecture as a named Testnet-Beta milestone

- State the 30/60/90-day milestone targets (Section 18)

- Note: Phase 1-4 is Testnet-Beta scope; Phase 5-8 is post-Beta

- Note: Mainnet consideration requires Gate 7 (Audit Gate) completion

- Cross-reference this specification document series as the implementation reference

## 21.5 Whitepaper Update Checklist

- 02-system-architecture.md: Section 3.7 added with DAG sublayer description

- 02-system-architecture.md: Section 3.2 updated to include DAG dissemination

- 02-system-architecture.md: Target data flow diagram added

- 03-proof-of-synergy-consensus.md: Section 6.9 added with cluster-local DAG description

- 03-proof-of-synergy-consensus.md: Section 6.3 updated with DAG scope = cluster boundary

- 03-proof-of-synergy-consensus.md: All 6 canonical DAG objects described (high-level)

- 09-threat-model-security-patent-relevant-effects.md: DAG threat section added

- 09-threat-model-security-patent-relevant-effects.md: Encrypted batch invariant explained

- 09-threat-model-security-patent-relevant-effects.md: Cross-reference to Security Spec v1.3 added

- 10-roadmap-and-strategic-outlook.md: DAG milestone added to roadmap

- 10-roadmap-and-strategic-outlook.md: Testnet-Beta vs. mainnet gate distinction noted

- All 4 whitepaper sections updated in both .md and .docx versions

- Whitepaper review: engineering lead reviews all whitepaper changes for accuracy

- Updated whitepaper sections committed to the synergy-network-whitepaper repository

SECTION 22 — FINAL REFERENCE

# Specification Cross-Reference and Authority

This section defines the authority hierarchy among all documents in the Synergy DAG integration specification set. In any conflict, the authority hierarchy below determines which document takes precedence.

| Priority | Document | Authority | Audience |
| --- | --- | --- | --- |
| 1 (Highest) | Synergy Network Security Specification v1.3 | Mandatory. Overrides any DAG design decision that conflicts with a v1.3 requirement. | All |
| 2 | ADR-001 through ADR-006 | Binding architecture decisions. Override whitepaper and planning documents. | All |
| 3 | DAG Validator Cluster Integration, Parts 1-3 (this document series) | Normative implementation reference. Overrides prior planning documents. | All |
| 4 | Synergy Network Whitepaper (updated sections) | Informational. Describes design intent for external audiences. Not normative. | External audiences |
| 5 (Reference) | Prior planning documents (Synergy_DAG_Validator_Cluster_Integration_Plan.docx, Synergy Testnet-Beta Cluster-Local DAG Sublayer Integration and DAG Security Enforcement Plan.docx, Synergy Network Cluster-Local Certified DAG Integration and Security Specification.docx) | Source material. Superseded by Parts 1-3 of this specification for implementation purposes. | Historical reference |

|  | Final Statement of Completeness This three-part specification (Part 1: Architecture & Design, Part 2: Implementation Roadmap & Security Enforcement, Part 3: Deployment, Operations & Deliverables) constitutes the complete, consolidated, and binding implementation reference for DAG integration into Synergy Network validator clusters. No aspect of the DAG integration is undocumented in this series. All implementation work begins from this specification, not from prior planning documents. |
| --- | --- |

SYNERGY NETWORK DAG Validator Cluster Integration Part 3 of 3 — Deployment, Operations & Deliverables Compliant with: Synergy Network Security Specification v1.3